## Mã Hóa Ứng Dụng
Status Tracker
|  | Assign | Start Date | End Date | Status | Note
1.Pre-Build
1.1 | Setup enviorment | Teams | 14/3/2021 | 14/3/2021 | Completed
2.In Process
2.1 | Build UI | Trường | 14/3/2021 | 14/3/2021 | Completed
2.2 | Ceasar | Trường | 14/3/2021 | 14/3/2021 | Completed
2.3 | Bảng chữ đơn | Trí | 14/3/2021 | 16/3/2021 | Completed
2.4 | PlayFair | Trường | 14/3/2021 | 16/3/2021 | Completed
2.5 | Vegenere | Dậu | 14/3/2021 | 17/3/2021 | Completed
2.6 | Chuyển dịch dòng | Dậu, Trí | 17/3/2021 | 25/3/2021 | Completed | Trí Encryption, Dậu Decryption
3.Build
3.1 | Merge All Function | Trường | 26/3/2021 | 26/3/2021 | Completed
3.2 | Test round 1 | Trí ,Trường | 23/3/2021 | 23/3/2021 | Completed
3.3 | Test round 2 | Dậu, Trường
3.4 | Review code | Teams | 26/3/2021 | 26/3/2021 | Completed
3.5 | Manual notebook | Teams |  |  |  | Base on 2. In Process, Done for Tri Truong
4.Relase